## Sheet1
Task ID | Task Name | Task Description | Estimated Start Time | Estimated Finish Time | Total Hour(s) | Actual Start Time | Actual Finish Time | Assigned To | Color Codes
1 | Plan The Project | Plan Out What We Will Base The Project On: Online Shoe Shop (Kix) | 2016-03-23 | 2016-03-23 | 2 Hour(s) | 2016-03-23 | 2016-03-23 | Camden & Brandon | Completed
2 | Design Logo | Design Logo For The Online Shoe Shop (Kix) | 2016-03-23 | 2016-03-23 | 1 Hour(s) | 2016-03-23 | 2016-03-23 | Brandon | In Progress
3 | Find Template | Find & Download Template To Get Us Started | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | 2016-03-31 | Camden & Brandon | Incomplete
4 | Plan Out Home Page | Plan Out The Home Page For Kix | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | Not There Yet | Camden & Brandon | Cancelled
5 | Develop Home Page | Develop The Home Page For Kix | 2016-03-31 | 2016-04-04 | 3 Hour(s) | 2016-03-31 | Not There Yet | Camden & Brandon | Halt Task
6 | Set-Up MySQL Database | Set-Up The Database For Kix Website (groupproject) | 2016-04-04 | 2016-04-04 | 0.5 Hour(s) | Not There Yet | Not There Yet | Camden & Brandon | Unknown Time
7 | Find Shoes | Find Shoes For The Store: Nike, Addidas | 2016-04-04 | 2016-04-04 | 0.5 Hour(s) | Not There Yet | Not There Yet | Camden & Brandon | Priority
8 | Call Center Project | Call Center Project: | 2016-03-31 | 2016-05-16 | Many Hours | 2016-03-31 | Not There Yet | Camden & Brandon
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29