## Sheet1
Task ID | Task Name | Task Description | Estimated Start Time | Estimated Finish Time | Total Hour(s) | Actual Start Time | Actual Finish Time | Assigned To | Color Codes
1 | Plan The Project | Plan Out What We Will Base The Project On: Online Shoe Shop (Kix) | 2016-03-23 | 2016-03-23 | 2 Hour(s) | 2016-03-23 | 2016-03-23 | Camden & Brandon | Completed
2 | Design Logo | Design Logo For The Online Shoe Shop (Kix) | 2016-03-23 | 2016-03-23 | 1 Hour(s) | 2016-03-23 | 2016-03-23 | Brandon | In Progress
3 | Find Template | Find & Download Template To Get Us Started | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | 2016-03-31 | Camden & Brandon | Incomplete
4 | Plan Out Home Page | Plan Out The Home Page For Kix | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | Not There Yet | Camden & Brandon | Cancelled
5 | Develop Home Page | Develop The Home Page For Kix | 2016-03-31 | 2016-04-04 | 3 Hour(s) | 2016-03-31 | Not There Yet | Camden & Brandon | Halt Task
6 | Set-Up MySQL Database | Set-Up The Database For Kix Website (groupproject) | 2016-04-04 | 2016-04-04 | 0.5 Hour(s) | Not There Yet | Not There Yet | Camden & Brandon | Unknown Time
7 | Find Shoes | Find Shoes For The Store: Nike, Addidas | 2016-04-04 | 2016-04-04 | 0.5 Hour(s) | Not There Yet | Not There Yet | Camden & Brandon | Priority
8 | Call Center Project | Call Center Project: | 2016-03-31 | 2016-05-16 | Many Hours | 2016-03-31 | Not There Yet | Camden & Brandon
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Task ID | Task Name | Task Description | Estimated Start Time | Estimated Finish Time | Total Hour(s) | Actual Start Time | Actual Finish Time | Assigned To
1 | Due Date | Due Date For Project Is May 15, 2016 | Start Project 31-Mar-16 | Finish Project 28-Apr-16 | N/A | Started 31-Mar-16 | N/A | Camden & Brandon | Color Codes
2 | Review SQL File | Study The SQL File's Contents For The Call Center Project | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | 2016-03-31 | Camden & Brandon | Completed
3 | Review Index File | Study The Index File Contents For The Call Center Project | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | 2016-03-31 | Camden & Brandon | In Progress
4 | Import SQL To Database | Import SQL File To The Database, Get Database Set-Up | 2016-04-04 | 2016-04-04 | 0.5 Hour(s) | Not There Yet | Not There Yet | Camden | Incomplete
5 | Review Under Construction PHP File | Study The Under Construction PHP File, See What's Needed | 2016-04-04 | 2016-04-04 | 0.5 Hour(s) | 2016-04-04 | 2016-04-04 | Camden & Brandon | Cancelled
6 | Go Over Objectives In Document | Read Over Doc, Input And Assign Tasks | 2016-03-31 | 2016-03-31 | 0.5 Hour(s) | 2016-03-31 | 2016-03-31 | Camden & Brandon | Halt Task
7 | Connect CSS To Index | Connect Index To The CSS To Display Styles | 2016-03-31 | 2016-03-31 | 0.1 Hour(s) | 2016-03-31 | 2016-03-31 | Brandon | Unknown
8 | Undefined Var In Manage Customers | Fix Bug In Customer Search Page | 2016-04-04 | 2016-04-04 | 1 Hour(s) | Not There Yet | Not There Yet | Camden | Priority
9 | Created Github Project | Upload What We Have So Far To Github | 2016-03-31 | 2016-03-31 | 0.1 Hour(s) | 2016-03-31 | 2016-03-31 | Camden | Information
10 | Uplaod Files To GitHub | Uplaod Files To GitHub Repo | 2016-03-31 | 2016-03-31 | 0.1 Hour(s) | 2016-03-31 | 2016-03-31 | Brandon
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30